## Cover
QA Report
Sprint | : | 1
Project | : | Data for Road Incident Visualization Evaluation and Reporting (DRIVER)
Build | : | Build Virsion
Date | : | 2023-09-29
Reporter | : | Rifat Shadman

## Release Summary
DRIVER 1.0.0 Summary Report
Release Info |  | Browser & Device List
Release Name | Data for Road Incident Visualization Evaluation and Reporting (DRIVER) | # | Desktop web Browser | Version
Version Name | 1.0.0 | 1 | Google Chrome for Windows | 117.0.5938.92
Release Topic | Manual Testing for DRIVER
Start Date | 19/09/2023
End Date | 27/09/2023
QA Release Date | 29/09/2023
Release Status | NA
Released By | Rifat Shadman
Prepared By | Rifat Shadman
Verified By | Abdul Qadir
Executed Test Type:
1 | Functional
2 | GUI
Non Executed Test Type:
1 | API
2 | Database
3 | Security

## Functionality Verification
DRIVER 1.0.0 Checklist
# | Module | TL Confirmation | Verified by QA | Status (by QA) | SE/TL Comment | QA Comment
1 | Login | Yes | Yes | OK | OK | All the testcases are passed
2 | Dashboard | Yes | Yes | NG | NG | #479903
3 | My Account | Yes | Yes | OK | OK | All the testcases are passed
4 | Map | Yes | Yes | NG | NG | #479557 #479577
5 | Record List | Yes | Yes | NG | NG | #479557 #479577 #479904
6 | Add A Record | Yes | Yes | NG | NG | #479993 #479994
7 | Manage Duplicate Records | Yes | Yes | NG | NG | #479521
[N.B: We have checked all screens and found some major and minor issues, these are posted in Jira]

## Graphical Report
Test Case Execution Report
| Build Version No: | Build Virsion
| Total Test cases: | 125
| Test Environments (Browsers): | 1
| Total Executable test cases: | 122
| Test Cases Executed: | 119
| Passed: | 112
| Failed: | 7
| NA: | 6
| WIP: | 0
| Total Reported Bugs : | 7
| New | 7
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 0
| Open | 0
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Blocker | 0
| Critical | 0
| Major | 3
| Minor | 4
| Trivial | 0
| Total: | 7
| Reported Bugs : (All Sprints) | 7
| New | 7
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 0
| Open | 0
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Low | 1
| Medium | 3
| High | 0
| Urgent | 0
| Immediate | 3
| Total: | 7
Step-2: Sprint#1 Bug summary
Step-2: Sprint#1 Bugs Severity:
Total Bug summary
Total Bugs (Priority wise):

## Bug_list
Sprint#1 Bug List
Bug Type | Quantity
UI: | 2
Functional: | 5
Total: | 7
# | Bug ID | Bug Summary | Status | Priority | Severity
1 |  | Total Loss amount format does not follow the format specified in the requirements | New | Low | Minor
2 |  | View and Edit buttons are broken and overlap with each other | New | Medium | Minor
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | #479557 | Wrong Date Format in both "To" and "From" fields in Occured Date filter | New | Immediate | Major
2 | #479577 | Typing Day and Month after selecting them does not work as intended | New | Immediate | Major
3 |  | Verify if Number of Driver Casualties, Passenger Casualties, and Pedestrian Casualties accepts values ranging from 0 to 100 instead of 0 to 150. | New | Medium | Minor
4 |  | VEHICLE REGISTRATION NUMBER field accepts text string when it should be numeric. | New | Medium | Minor
5 | #479521 | "Manage Duplicate Records" page does not display any information about potential duplicate even when there are duplicate entries available on the record list. | New | Immediate | Major
Functional Bugs:
Step-2: Sprint#1- Bug summary
UI Bugs:

## Bug_trend
Sprint | Test case | Bugs | Resolved | Trend
Sprint#1 | 125 | 7 | 0 | 0

## Defect density
Sprint | Effort | Defect | Defect density | Defect density
Sprint#1 | 24 | 7 | 29.17% | 29.17%