## Cover Page
Test Execution Cover Page for DRIVER
Test Summary
Test Environment
| Total Test Case | 125
| OK | 112 | `
| NG | 7
| NA | 6
Release Info
| Application Name | Data for Road Incident Visualization Evaluation and Reporting (DRIVER)
| Start Date | 20-09-2023
| End Date | 27-09-2023
| QA Release Date | 27-09-2023
| Released By | Rifat Shdaman
| Verified By | Abdul Qadir

## Revision History
SL. | Version | Change | Author | Date | Reviewed by
1 | 1.0.0 | Initial Release | Rifat Shadman | 26-09-2023 | Abdul Qadir
2 | 1.0.1 | Cover page, Remarks | Rifat Shadman | 27-09-2023 | Abdul Qadir

## Functional
[Project Name] GUI Test Cases for Web Domain
No. | Function Name | No. | Major Category | Priority | Result | Remark
TC_FN_001 | Login | TC_FN_001 | Login | High | OK
TC_FN_002 |  | TC_FN_002 | Login | High | OK
TC_FN_003 |  | TC_FN_003 | Login | High | OK
TC_FN_004 | Dashboard | TC_FN_004 | Dashboard | Normal | OK
TC_FN_005 |  | TC_FN_005 | Dashboard | Normal | OK
TC_FN_006 |  | TC_FN_006 | Dashboard | Normal | OK
TC_FN_007 |  | TC_FN_007 | NAVBAR | Normal | OK
TC_FN_008 |  | TC_FN_008 | NAVBAR | Normal | OK
TC_FN_009 |  | TC_FN_009 | Dashboard Map | Normal | OK
TC_FN_010 |  | TC_FN_010 | Blackspots by Severity | Normal | OK
TC_FN_011 |  | TC_FN_011 | Incidents: Last Two Weeks | Normal | OK
TC_FN_012 |  | TC_FN_012 | Dashboard Map Layer | Normal | OK
TC_FN_013 |  | TC_FN_013 | Dashboard | Normal | OK
TC_FN_014 |  | TC_FN_014 | Dashboard | Normal | OK
TC_FN_015 |  | TC_FN_015 | Dashboard | Normal | OK
TC_FN_016 |  | TC_FN_016 | Dashboard | Normal | OK
TC_FN_017 |  | TC_FN_017 | Dashboard | Normal | OK
TC_FN_018 | My Account | TC_FN_018 | My Account | Normal | OK
TC_FN_019 | Map | TC_FN_019 | Map Filters | Normal | OK
TC_FN_020 |  | TC_FN_020 |  | Normal | OK
TC_FN_021 |  | TC_FN_021 |  | Normal | OK
TC_FN_022 |  | TC_FN_022 |  | Normal | OK
TC_FN_023 |  | TC_FN_023 |  | Normal | OK
TC_FN_024 |  | TC_FN_024 |  | Normal | OK
TC_FN_025 |  | TC_FN_025 |  | Normal | OK
TC_FN_026 |  | TC_FN_026 |  | Normal | OK
TC_FN_027 |  | TC_FN_027 | Control Layer Toggle | Normal | OK | Although the street map is properly labeled, the satellite map has no label on it at all. This can have a negative impact.
TC_FN_028 |  | TC_FN_028 |  | Normal | OK
TC_FN_029 |  | TC_FN_029 | Zooming | Normal | OK
TC_FN_030 |  | TC_FN_030 |  | Normal | OK
TC_FN_031 |  | TC_FN_031 | Layer Addition | Normal | OK
TC_FN_032 |  | TC_FN_032 |  | Normal | OK
TC_FN_033 |  | TC_FN_033 |  | Normal | OK
TC_FN_034 |  | TC_FN_034 |  | Normal | OK
TC_FN_035 |  | TC_FN_035 | Footer | Normal | OK
TC_FN_036 |  | TC_FN_036 |  | Normal | OK
TC_FN_037 |  | TC_FN_037 |  | Normal | OK
TC_FN_038 |  | TC_FN_038 |  | Normal | OK
TC_FN_039 |  | TC_FN_039 |  | Normal | OK
TC_FN_040 | Record List | TC_FN_040 | Record List | Normal | OK
TC_FN_041 |  | TC_FN_041 |  | Normal | NG | Date format is DD/MM/YYYY instead of MM/DD/YYYY
TC_FN_042 |  | TC_FN_042 |  | Normal | NG | Date format is DD/MM/YYYY instead of MM/DD/YYYY
TC_FN_043 |  | TC_FN_043 |  | Normal | OK | Individual filters for Driver Sex and Passenger Sex is not present. Instead, there is one filter named Sex, which creates ambiguity.
TC_FN_044 |  | TC_FN_044 |  | Normal | OK
TC_FN_045 |  | TC_FN_045 |  | Normal | OK
TC_FN_046 |  | TC_FN_046 |  | Normal | OK
TC_FN_047 |  | TC_FN_047 |  | Normal | OK
TC_FN_048 |  | TC_FN_048 |  | Normal | OK
TC_FN_049 |  | TC_FN_049 |  | Normal | OK
TC_FN_050 |  | TC_FN_050 |  | Normal | OK
TC_FN_051 | Add A Record | TC_FN_051 | Add a Record | Normal | OK
TC_FN_052 |  | TC_FN_052 | Incident Location and Time | Normal | OK
TC_FN_053 |  | TC_FN_053 |  | Normal | OK
TC_FN_054 |  | TC_FN_054 |  | Normal | OK
TC_FN_055 |  | TC_FN_055 |  | Normal | OK
TC_FN_056 |  | TC_FN_056 |  | Normal | Not Tested
TC_FN_057 |  | TC_FN_057 |  | Normal | OK
TC_FN_058 |  | TC_FN_058 |  | Normal | OK
TC_FN_059 |  | TC_FN_059 |  | Normal | OK
TC_FN_060 |  | TC_FN_060 |  | Normal | OK
TC_FN_061 |  | TC_FN_061 | RCF | Normal | OK
TC_FN_062 |  | TC_FN_062 |  | Normal | OK
TC_FN_063 |  | TC_FN_063 |  | Normal | OK | User can upload images more than 1 megabyte in size. This can put pressure on the database in the long run.
TC_FN_064 |  | TC_FN_064 |  | Normal | OK
TC_FN_065 |  | TC_FN_065 |  | Normal | OK | NUMBER of ANIMAL DRAWN, OTHER INVOLVED fields don't have a limit. All the other fields throw error for invalid inputs and accept only the valid inputs.
TC_FN_066 |  | TC_FN_066 |  | Normal | OK
TC_FN_067 |  | TC_FN_067 |  | Normal | OK
TC_FN_068 |  | TC_FN_068 | ARF | Normal | OK
TC_FN_069 |  | TC_FN_069 |  | Normal | OK
TC_FN_070 |  | TC_FN_070 |  | Normal | OK
TC_FN_071 |  | TC_FN_071 |  | Normal | OK
TC_FN_072 |  | TC_FN_072 |  | Normal | OK
TC_FN_073 |  | TC_FN_073 |  | Normal | OK
TC_FN_074 |  | TC_FN_074 |  | Normal | NG | Upper limit for all three fields in the build is 100 instead of 150.
TC_FN_075 |  | TC_FN_075 |  | Normal | OK
TC_FN_076 |  | TC_FN_076 |  | Normal | OK
TC_FN_077 |  | TC_FN_077 |  | Normal | OK
TC_FN_078 |  | TC_FN_078 | VEHICLES | Normal | OK
TC_FN_079 |  | TC_FN_079 |  | Normal | OK
TC_FN_080 |  | TC_FN_080 |  | Normal | OK
TC_FN_081 |  | TC_FN_081 |  | Normal | NG | Vehicle registration number is accepting text fields
TC_FN_082 |  | TC_FN_082 |  | Normal | OK
TC_FN_083 |  | TC_FN_083 |  | Normal | OK
TC_FN_084 |  | TC_FN_084 |  | Normal | OK
TC_FN_085 |  | TC_FN_085 | PASSENGER PEDESTRIAN | Normal | OK
TC_FN_086 |  | TC_FN_086 |  | Normal | OK
TC_FN_087 |  | TC_FN_087 |  | Normal | OK
TC_FN_088 |  | TC_FN_088 |  | Normal | OK
TC_FN_089 |  | TC_FN_089 |  | Normal | OK
TC_FN_090 |  | TC_FN_090 |  | Normal | OK
TC_FN_091 |  | TC_FN_091 | CONTRIBUTORY FACTORS | Normal | OK
TC_FN_092 |  | TC_FN_092 |  | Normal | OK
TC_FN_093 |  | TC_FN_093 | SAVE INCIDENT | Normal | Not Tested | Not Specified in the SRS
TC_FN_094 |  | TC_FN_094 |  | Normal | Not Tested | Not Specified in the SRS
TC_FN_095 |  | TC_FN_095 | Mange Duplicate Records | Normal | OK
TC_FN_096 |  | TC_FN_096 |  | Normal | NG | No data is being fetched even when potential duplicate records are available in the record list
TC_FN_097 |  | TC_FN_097 |  | Normal | NA | Could not be executed for failure of TC_FN_096
TC_FN_098 |  | TC_FN_098 |  | Normal | NA | Could not be executed for failure of TC_FN_096
TC_FN_099 |  | TC_FN_099 |  | Normal | NA | Could not be executed for failure of TC_FN_096

## GUI
[Project Name] GUI Test Cases for Web Domain
No. | Function Name | No. | Priority | Result | Remark
TC_GUI_001 | Login | TC_GUI_001 | Normal | OK
TC_GUI_002 |  | TC_GUI_002 | Normal | OK
TC_GUI_003 | Dashboard | TC_GUI_003 | Normal | OK
TC_GUI_004 |  | TC_GUI_004 | Normal | OK
TC_GUI_005 |  | TC_GUI_005 | Normal | OK
TC_GUI_006 |  | TC_GUI_006 | Normal | OK
TC_GUI_007 |  | TC_GUI_007 | Normal | OK
TC_GUI_008 |  | TC_GUI_008 | Normal | NG | Built format is BDT100Lakhs instead of 100,000 BDT
TC_GUI_009 |  | TC_GUI_009 | Normal | OK
TC_GUI_010 | Map | TC_GUI_010 | Normal | OK
TC_GUI_011 |  | TC_GUI_011 | Normal | OK
TC_GUI_012 |  | TC_GUI_012 | Normal | OK
TC_GUI_013 |  | TC_GUI_013 | Normal | OK
TC_GUI_014 | Record List | TC_GUI_014 | Normal | NG | Buttons are broken and overlap
TC_GUI_015 |  | TC_GUI_015 | Normal | OK
TC_GUI_016 |  | TC_GUI_016 | Normal | OK
TC_GUI_017 |  | TC_GUI_017 | Normal | OK
TC_GUI_018 | Add a Record | TC_GUI_018 | Normal | OK
TC_GUI_019 |  | TC_GUI_019 | Normal | OK
TC_GUI_020 |  | TC_GUI_020 | Normal | OK
TC_GUI_021 |  | TC_GUI_021 | Normal | OK
TC_GUI_022 |  | TC_GUI_022 | Normal | OK
TC_GUI_023 |  | TC_GUI_023 | Normal | OK
TC_GUI_024 | Manage Duplicate Records | TC_GUI_024 | Normal | OK
TC_GUI_025 |  | TC_GUI_025 | Normal | OK
TC_GUI_026 |  | TC_GUI_026 | Normal | OK

## Notes
Notes
Test Results
For the test results, it will basically following rules.
・Date confirmed
・Confirmation's name
・Confirmation terminal
It described to confirm the daily.
・Test results
Is, "OK", "NG", "NA".
「OK」：If the operation of the expected behavior as could be confirmed
「NG」：If the operation of the expected behavior could not be confirmed
「NA」：If the test carried out is not possible/ Not executed.
※ NG Detailed generating procedure of the bug is recoreded in Redmine with appropiate test evidence.